## Work Order Book
S. No. | Work Order No. | Work Order Date | Client Name | Project Name | Project Location | Lights | Work Order Value | Start Date | Completion Date | Project Manager | Responsible Person | Status | Remarks
1 | 11390 | 2026-03-18 | SUNFEED ECOSOLUTIONS INDIA PVT LTD | SOLAR STREET LIGHT | PANCHKULA AND YAMNANAGAR | 179.nos | 3043000 | IN PROCESS | IN PROCESS | UMESH KHATTER | UMESH KHATTER | COMPLETED
2 | 11579 | 2026-03-24 | SUNFEED ECOSOLUTIONS INDIA PVT LTD | SOLAR STREET LIGHT | GURGAON AND REWARI | 169.nos | 2873000 | 2026-06-11 | 2026-06-18 | UMESH KHATTER | UMESH KHATTER | COMPLETED
3 | 776 | 2026-05-04 | SUNFEED ECOSOLUTIONS INDIA PVT LTD | SOLAR STREET LIGHT | YAMNANAGAR,CHARKHI DADRI,AMBALA,JHAJJAR,GURUGRAM | 927.nos | 15759000 | IN PROCESS | IN PROCESS | UMESH KHATTER | UMESH KHATTER | IN PROCESS
4 | 3396 | 2026-07-02 | SUNFEED ECOSOLUTIONS INDIA PVT LTD | SOLAR STREET LIGHT | AMBALA,REWARI,KAITHAL | 227.nos | 3859000 | IN PROCESS | IN PROCESS | UMESH KHATTER | UMESH KHATTER | IN PROCESS
5 | 10521 | 2026-02-18 | SUNFEED ECOSOLUTIONS INDIA PVT LTD | SOLAR STREET LIGHT | AMBALA,PANCHKULA | 220.nos | 3740000 | 2026-03-20 | 2026-04-04 | UMESH KHATTER | UMESH KHATTER | COMPLETED
6 | 10060 | 2026-02-04 | SUNFEED ECOSOLUTIONS INDIA PVT LTD | SOLAR STREET LIGHT | AMBALA,REWARI,KURUSHETRE | 255.nos | 4335000 | 20-.3-2026 | 2026-04-10 | UMESH KHATTER | UMESH KHATTER | COMPLETED
7 | 10570 | 2026-02-19 | SUNFEED ECOSOLUTIONS INDIA PVT LTD | SOLAR STREET LIGHT | PANCHKULA AND KURUSHETRE | 570.nos | 10200000 | 20-.3-2026 | 2026-04-15 | UMESH KHATTER | UMESH KHATTER | COMPLETED
8 | 1712 | 2026-02-05 | SUNFEED ECOSOLUTIONS INDIA PVT LTD | SOLAR STREET LIGHT | GURGAON | 9.nos | 153000 | 2026-03-05 | 2026-03-05 | UMESH KHATTER | UMESH KHATTER | COMPLETED
9 | 11350 | 2026-03-16 | SUNFEED ECOSOLUTIONS INDIA PVT LTD | SOLAR STREET LIGHT | REWARI | 52.nos | 884000 | 2026-03-31 | 2026-04-03 | UMESH KHATTER | UMESH KHATTER | COMPLETED
10 | 3755 | 2026-07-20 | SUNFEED ECOSOLUTIONS INDIA PVT LTD | SOLAR STREET LIGHT | REWARI,JHAJJAR,KAITHAL,PANCHKULA | 189.nos | 3213000 |  |  | UMESH KHATTER | UMESH KHATTER |  | PDI PENDING
11 | 335 | 2026-07-07 | SUNFEED ECOSOLUTIONS INDIA PVT LTD | SOLAR STREET LIGHT | KAITHAL | 56.nos | 952000 |  |  | UMESH KHATTER | UMESH KHATTER |  | PDI PENDING
12 | 638 | 2026-02-04 | SUNFEED ECOSOLUTIONS INDIA PVT LTD | SOLAR STREET LIGHT | KURUSHETRA | 14.NOS | 238000 | 2026-03-31 | 2026-04-01 | UMESH KHATTER | UMESH KHATTER | COMPLETED